## Timeline A
Sample Timeline*
Timeline for Seacology Project located in ____________
DATES | ACTIVITY
2009-04-01 | Coordination with villages and local government to finalize project and conservation area details
2009-05-01 | Sign of grant agreement
2009-05-10 | Payment from Seacology: 1st installment of ~$15,000 (75% of grant amount)
May 10-15 | Order construction materials
May 15-31 | Receive materials and begin preliminary construction, including foundation preparation
June 1 – September 30 | Construction of community hall
2009-09-01 | Provide Seacology with progress report, financial report, photos, and request for next installment payment
2009-09-15 | Payment from Seacology: 2nd installment of ~$5,000 (25% of grant amount)
September 15-31 | Order finishing materials, including paint, tiles, etc
October | Perform finishing touches on community hall, including paint, tiling, etc
2009-11-15 | Opening ceremony for completed community hall
* This also includes a sample grant payment schedule.

## Timeline B
Sample Timeline
Timeline for Seacology Project located in ____________
Work Breakdown Structure | PERIOD |  | CONSTRUCTION SCHEDULE
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6
Tasks | No | Unit | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 Purchase of Materials | 5 | Days
2 Clearing | 3 | Days
3 Transport Materials | 5 | Days
4 Excavation
4.1 Well | 4 | Days
4.2 Foundation | 3 | Days
5 Foundation (Posts and Reinforcements) | 4 | Days
6 Plumbing
6.1 Water Pump | 1 | Days
6.2 Sewage | 5 | Days
6.3 Internal | 3 | Days
7 Flooring | 5 | Days
8 Concrete Partitions | 6 | Days
9 Trusses | 4 | Days
10 Roofing | 7 | Days
11 Electrical Lines | 7 | Days
12 Wood Partitions, Windows and other woodworks | 9 | Days
13 Solar Panels | 3 | Days
14 Railings | 4 | Days
15 Concrete Finishing | 4 | Days
16 Sanding and Painting | 4 | Days
17 Cleaning | 2 | Days
Total | 6 | Weeks

## Timeline C
Sample Timeline
Timeline for Seacology Project located in ____________
PROJECT ACTIVITIES | Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1. Funding Availability | X
2. Gathering of coral heads and rocks | X | X | X | X | X | X | X | X
3. Contract local Rock Mason Expert | X
4. Purchase of Materials (cement,sand,etc) | X |  | X |  | X |  | X
5. Construction | X | X | X | X | X | X | X | X
6. Fill Materials (transport to site) |  |  | X |  | X |  | X | X
7. Purchase of Materials for Toilet |  |  |  | X |  | X
8. Construction of Toilet, Septic & Leaching |  |  |  | X | X | X | X
9. Project Final Inspection & Punch List | [7 empty] | X
10.Project Completion Certification | [7 empty] | X

## Budget A
Sample Budget
Budget for Seacology Project located in ____________
Project Name:
Date:
Local Currency:
In local currency
Item(s) | Description | Quantity | Unit Price | Total Price
Purchase of Land (for conservation area or for project benefit)
Construction Materials (for project benefit)
Transportation/Shipping/Freight (for construction materials)
Computers & Electronics
Labor & Professional Services (for construction - carpenters, plumbers, builders, etc)
Facility & Program Expenses (office supplies, furnishings, solar panels, water tanks, medical supplies, educational materials, scholarships, livelihood training costs etc)
Conservation Costs (mapping, surveillance equipment, training or rangers, etc)
Replanting and Rehabilitation (costs of seedlings, tools, labor, nursery expenses)
Meeting & Planning Expenses (costs of meetings, transporting people to meetings, etc.)
Miscellaneous (everything else)
Subtotal:
Administrative Overhead:
Total:

## Budget B
Sample Budget
Budget for Seacology Project located in ____________
Building Foundation for the Bridge
cement | 1700
rebar - various sizes | 1300
gravel and sand | 2100
lumber – various sizes | 5600
transportation of materials to site | 1500
miscellaneous supplies (nails, tools, etc) | 200
heavy equipment rental | 2000
Construction of Bridge, Roofing, etc.
roofing materials | 2000
miscellaneous supplies (nails, tools, etc) | 1000
transportation of materials to site | 2000
lumber - various sizes | 4000
sealant | 500
Other costs
Office supplies | 1000
Fuel and other miscellaneous supplies | 3000
Utilities | 3000
Administrative overhead | 3000
TOTAL | 33900
Equivalent in US dollars | 42181.8378

## Budget C
Sample Budget
Budget for Seacology Project located in ____________
Material | Price Unit | Quantity | Total Cost
Cement | 990 | 150 | 148500
Mesh Wire | 8750 | 25 | 218750
Steel Rod (12 mm) | 1530 | 70 | 107100
Steel Rod (10 mm) | 1065 | 120 | 127800
Steel Rod (6mm) | 295 | 90 | 26550
Blocks No 15 | 170 | 1380 | 234600
Blocks No 10 | 150 | 120 | 18000
Timbers (NZ Pine) |  |  | 0
5mm x 15mm x 6 m | 3130 | 38 | 118940
5mmx10mm x6m | 2050 | 55 | 112750
3mmx25mmx 6m | 5730 | 14 | 80220
5mmx5mmx 6m | 975 | 60 | 58500
Hardwood Frames | 2300 | 25 | 57500
Masonite | 1730 | 60 | 103800
Sisilation Durafoil | 9715 | 4 | 38860
Roofing Nails | 40 | 500 | 20000
Nails: |  |  | 0
5 Inch | 7000 | 1 | 7000
4 Inch | 7000 | 1 | 7000
3 Inch | 7000 | 1 | 7000
2 Inch | 7000 | 1 | 7000
1 Inch | 7000 | 1 | 7000
Cyclone Straps | 6745 | 2 | 13490
Cooper Pipe | 10800 | 1 | 10800
Black Turbuline | 11750 | 2 | 23500
Plywood | 5432 | 15 | 81480
Iron Roofing (Galvanised) | 960 | 232 | 222720
Flashing | 2980 | 10 | 29800
Ridging | 2980 | 5 | 14900
Paints (interior) | 27600 | 4 | 110400
Paints (Exterior) | 27600 | 3 | 82800
Boult Nuts | 167 | 18 | 3006
Door Hinges | 990 | 3 | 2970
Window Hinges | 360 | 8 | 2880
Entrance Locks (doors) | 2500 | 3 | 7500
Pin locks (windows) | 357 | 24 | 8568
Toilet Set | 14990 | 1 | 14990
Tie Wire | 400 | 6 | 2400
Water Tanks | 163125 | 1 | 163125
Polytene water pipe | 150 | 20 | 3000
Doors | 10800 | 3 | 32400
Basin | 6320 | 1 | 6320
2343919
Labour |  |  | 500000
Freight |  |  | 300000
TOTAL BUDGET |  | in VUV | 3143919
Equivalent in US dollars |  |  | 33168.3455

## Budget D
Sample Budget
Budget for Seacology Project located in ____________
Item | Description | Cost per unit | Number of units | Total
Bouys for demarcation | Concrete weight 130 kgs, buoys with 10m chain | 30000 | 10 | 300000
Installation Cost | Transport to the site and installation | 100000 | 1 | 100000
Boat Moorings | Concrete weight 150 kgs, buoys, with 12m chain | 15000 | 5 | 75000
Installation Cost | Transport to the site and installation | 100000 | 1 | 100000
Snorkelling gear | Dive mask (Speedo type) snorkle included & wetsuits | 8500 | 12 | 102000
| Flippers and shoes | 3500 | 12 | 42000
Radio for communication | Marine VHF ICM, 5 handsets and accessories | 17500 | 5 | 87500
| Purchase of base set and installation | 30000 | 1 | 30000
Solar inverter system | Complete solar module system, sealed battery, power 8x6 watts, low energy bulbs, bracket for mounting the panels plus transport included. | 350000 | 1 | 350000
Construction of two bandas for patrols and monitoring | Two bandas for patrols and monitoring of turtle nesting sites and closed areas | 200000 | 2 | 400000
Meetings and administration expenses | Monthly meetings to review project progress, monitoring and progress reporting | 7500 | 10 | 75000
Patrols and monitoring | Purchase of scouts uniforms, torches, raincoats etc | 75000 | 1 | 75000
Miscellaneous |  |  |  | 200000
TOTAL |  |  |  | 1936500
Equivalent in US dollars |  |  |  | 16570.2432

## Budget E
Sample Budget
Budget for Seacology Project located in ____________
Fresh water pipe system
No | Description | Quantity |  | Unit Price |  |  | Total | From Seacology (in Rp) | From Seacology (in USD) | From other sources (in Rp)
|  |  |  | (in Rp) |  |  | (in Rp)
A. | Tools and Materials
1 | Metal cuffs - straight
| - Size 3" | 45 |  | 35000 |  |  | 1575000 | 1575000 | 175 | 0
| - Size 2" | 80 |  | 22500 |  |  | 1800000 | 1800000 | 200 | 0
| - Size 1 1/2" | 85 |  | 15000 |  |  | 1275000 | 1275000 | 141.6667 | 0
| - Size 1" | 150 |  | 12500 |  |  | 1875000 | 1875000 | 208.3333 | 0
| - Size 3/4" | 125 |  | 10500 |  |  | 1312500 | 1312500 | 145.8333 | 0
| - Size 1/2" | 125 |  | 8000 |  |  | 1000000 | 1000000 | 111.1111 | 0
2 | Metal cuffs – L shape | [8 empty] | 0
| - Size 3" | 25 |  | 40000 |  |  | 1000000 | 1000000 | 111.1111 | 0
| - Size 2" | 25 |  | 35000 |  |  | 875000 | 875000 | 97.2222 | 0
| - Size 1 1/2" | 60 |  | 22500 |  |  | 1350000 | 1350000 | 150 | 0
| - Size 1" | 50 |  | 17500 |  |  | 875000 | 875000 | 97.2222 | 0
| - Size 3/4" | 50 |  | 15000 |  |  | 750000 | 750000 | 83.3333 | 0
| - Size 1/2" | 50 |  | 11000 |  |  | 550000 | 550000 | 61.1111 | 0
3 | Metal cuffs – T shape | [8 empty] | 0
| - Size 3" | 15 |  | 35000 |  |  | 525000 | 525000 | 58.3333 | 0
| - Size 2" | 20 |  | 30000 |  |  | 600000 | 600000 | 66.6667 | 0
| - Size 1 1/2" | 25 |  | 22500 |  |  | 562500 | 562500 | 62.5 | 0
| - Size 1" | 25 |  | 17500 |  |  | 437500 | 437500 | 48.6111 | 0
| - Size 3/4" | 50 |  | 15000 |  |  | 750000 | 750000 | 83.3333 | 0
| - Size 1/2" | 50 |  | 11000 |  |  | 550000 | 550000 | 61.1111 | 0
4 | Over Cuffs | [8 empty] | 0
| - Size 3" | 10 |  | 37500 |  |  | 375000 | 375000 | 41.6667 | 0
| - Size 2" | 10 |  | 30000 |  |  | 300000 | 300000 | 33.3333 | 0
| - Size 1 1/2" | 10 |  | 22500 |  |  | 225000 | 225000 | 25 | 0
| - Size 1" | 10 |  | 15000 |  |  | 150000 | 150000 | 16.6667 | 0
| - Size 3/4" | 50 |  | 15000 |  |  | 750000 | 750000 | 83.3333 | 0
5 | Faucets
| - Size 3" | 20 |  | 40000 |  |  | 800000 | 800000 | 88.8889 | 0
| - Size 2" | 20 |  | 32000 |  |  | 640000 | 640000 | 71.1111 | 0
| - Size 1 1/2" | 20 |  | 25000 |  |  | 500000 | 500000 | 55.5556 | 0
| - Size 1" | 20 |  | 20000 |  |  | 400000 | 400000 | 44.4444 | 0
6 | Nuts | [8 empty] | 0
| - Size 3" | 5 |  | 35000 |  |  | 175000 | 175000 | 19.4444 | 0
| - Size 2" | 5 |  | 32000 |  |  | 160000 | 160000 | 17.7778 | 0
| - Size 1 1/2" | 10 |  | 22500 |  |  | 225000 | 225000 | 25 | 0
| - Size 1" | 10 |  | 15000 |  |  | 150000 | 150000 | 16.6667 | 0
7 | Faucet | 100 |  | 22500 |  |  | 2250000 | 2250000 | 250 | 0
8 | Pipe tape | 400 |  | 4000 |  |  | 1600000 | 1600000 | 177.7778 | 0
9 | Pipes | [8 empty] | 0
| - Size 3" | 75 |  | 525000 |  |  | 39375000 | 39375000 | 4375 | 0
| - Size 2" | 90 |  | 350000 |  |  | 31500000 | 31500000 | 3500 | 0
| - Size 1 1/2" | 90 |  | 300000 |  |  | 27000000 | 27000000 | 3000 | 0
| - Size 1" | 130 |  | 200000 |  |  | 26000000 | 26000000 | 2888.8889 | 0
| - Size 3/4" | 150 |  | 140000 |  |  | 21000000 | 21000000 | 2333.3333 | 0
| - Size 1/2" | 150 |  | 115000 |  |  | 17250000 | 17250000 | 1916.6667 | 0
10 | Cement | 100 |  | 80000 |  |  | 8000000 | 7000000 | 777.7778 | 1000000
11 | Cement spoons | [8 empty] | 0
| - Small round | 5 |  | 20000 |  |  | 100000 | 100000 | 11.1111 | 0
| - Small pointed | 5 |  | 17500 |  |  | 87500 | 87500 | 9.7222 | 0
| - Large round | 5 |  | 17500 |  |  | 87500 | 87500 | 9.7222 | 0
| - Large pointed | 5 |  | 15000 |  |  | 75000 | 75000 | 8.3333 | 0
12 | Sand | 10 |  | 400000 |  |  | 4000000 | 2000000 | 222.2222 | 2000000
13 | Buckets | 25 |  | 20000 |  |  | 500000 | 500000 | 55.5556 | 0
14 | Shovel | 10 |  | 75000 |  |  | 750000 | 750000 | 83.3333 | 0
15 | Tools | 5 |  | 65000 |  |  | 325000 | 325000 | 36.1111 | 0
16 | Transportation | 1 |  | 2500000 |  |  | 2500000 | 2500000 | 277.7778 | 0
17 | Stones | 10 |  | 250000 |  |  | 2500000 | 1000000 | 111.1111 | 1500000
18 | Water tank (2x2x2) | 6 |  | 7500000 |  |  | 2500000 | 2500000 | 277.7778 | 0
S U B T O T A L (A) | [6 empty] | 209912500 | 205412500 | 22823.6111 | 4500000
B. | Labor
1 | Drawing costs |  | 1 |  | 5000000 | 5000000 |  | 5000000 | 555.5556 | 0
2 | Skilled Labor |  | 100 |  | 40000 | 4000000 |  | 2000000 | 222.2222 | 2000000 | US dollar equivalent from other sources
3 | Foreman |  | 90 |  | 75000 | 6750000 |  | 2500000 | 277.7778 | 4250000
4 | Casual labor 24 x 90 days |  | 2160 |  | 45000 | 97200000 |  | 60000000 | 6666.6667 | 37200000
S U B T O T A L (B) | [5 empty] | 112950000 |  | 69500000 | 7722.2222 | 43450000
TOTAL COST (A + B) | [5 empty] | 322862500 |  | 274912500 | 30544.8333 | 47950000 | 5327.7778
Exchange Rate based on Rp 9,000/USD 1